## Sheet1
Day
Start | 2024-04-22 | Final Brainstorm | Make Maven Framework, test if operational |  |  |  | DONE
| 2024-04-26 | Decide on front end framework. GUI? Spring Boot? JSP? Something else? | [5 empty] | Search for third party applications that can be used to enhance the data from the GeoDB Cities API. Ex: display longitude and latitude cordinates on map. |  | Maybe another api we can use additonally | DONE: used springboot, got a second API
| 2024-04-29 | Functional Template Front end |  | Working API calls, and basic data handling |  |  |  | REWORKED
| 2024-05-03 | Enhanced Methods for data handling |  |  | REWORKED | Attempt communication between porject and frontend |  |  | DONE
| 2024-05-06 | Establish proper communication between project and front end
| 2024-05-10 | Frontend design
| 2024-05-12 | Code review and bug fixes |  | Due date
*** The last few days are sparse because we expect delays with frontend implmentation and communication with front end as that was out area of failure in the midterm
*** Used AI for definition of an Agile Plan, but it didn't have the context to give any meanigful plan, this thing was made entirly by us